## Modules List
WAJENZI — MODULES LIST
PHASE 1 — Foundation & Core Operations (Oct 2024 – Apr 2025)
# | Module | Sub Module | Short Description | Settings | Reports | Implementation Period | Price (TZS) | Status
16 | Settings & Configuration | Company Setup | Company name, logo, TIN, address, letterhead | Company profile | — | Oct – Nov 2024 (Wk 1 – 5) | TZS 17,000,000 | Complete
|  | Roles & Permissions | Define roles with granular permission matrix | 25+ permission groups | Permission audit report
|  | Approval Workflows | Configure multi-level approval chains per document type | 20+ document types | Approval audit trail
|  | Numbering Sequences | Auto-numbering for invoices, POs, vouchers, etc. | Prefix and sequence config | —
|  | Email Configuration | SMTP setup for system emails and notifications | Email templates | —
|  | Backup & Maintenance | Database backup scheduling and system maintenance | Backup schedule | Backup log
2 | Employee Management | Employee Records | Full HR profiles: personal info, contracts, documents, photos | Employee fields config | Employee list report | Oct – Dec 2024 (Wk 3 – 10) | TZS 14,500,000 | Complete
|  | Employee Documents | Upload and manage employee certificates, IDs, contracts | Document types | —
|  | Emergency Contacts | Next-of-kin and emergency contact information | — | —
|  | Employment History | Track promotions, transfers, contract changes | — | Employment history report
|  | Employee Separation | Termination, resignation, retirement processing | Separation reasons | Separation report
5 | Finance & Accounting | Chart of Accounts | Full hierarchical account structure (assets, liabilities, equity, revenue, expenses) | Account types, categories | Trial balance | Nov 2024 – Feb 2025 (Wk 5 – 16) | TZS 26,000,000 | Complete
|  | Journal Entries | Double-entry journal with multi-line debit/credit | Entry types | Journal entry report
|  | Bank Accounts | Manage company bank accounts and balances | Bank list | Bank balance report
|  | Bank Reconciliation | Match bank statements with system transactions | — | Reconciliation report
|  | Petty Cash | Track petty cash disbursements and replenishments | Petty cash limits | Petty cash report
|  | Payment Vouchers | Approve and process payments to suppliers and staff | Approval workflow | Payment voucher report
|  | Receipts | Record and issue receipts for incoming payments | — | Receipt register
|  | Financial Statements | Income statement, balance sheet, cash flow | Fiscal year config | P&L, Balance Sheet, Cash Flow
|  | Imprest Requests | Issue and retire staff imprest with approval | Imprest limits | Imprest report
|  | Advance Salaries | Salary advances recovered via payroll | Advance limits | Advance report
|  | Allowances | Allowance subscriptions and payments to staff | Allowance types | Allowance report
|  | Beneficiary Accounts | Payee/beneficiary bank account register | — | —
|  | Financial Charges | Bank and finance charge categories and entries | Charge categories | Charges report
|  | Collections | Track receivable collections against clients | — | Collections report
|  | Exchange Rates | Multi-currency exchange rate management | Currency config | —
|  | System Ledgers | Cash, credit, capital and inventory control ledgers | Ledger config | Ledger reports
9 | Statutory Compliance | PAYE Processing | Pay-As-You-Earn tax calculation per TRA brackets | PAYE tax tables | PAYE monthly report | Dec 2024 – Jan 2025 (Wk 9 – 15) | TZS 17,000,000 | Complete
|  | NSSF Contributions | National Social Security Fund employer/employee contributions | NSSF rates | NSSF report
|  | WCF Contributions | Workers' Compensation Fund calculations | WCF rates | WCF report
|  | SDL Contributions | Skills Development Levy processing | SDL rates | SDL report
|  | NHIF Contributions | National Health Insurance Fund deductions | NHIF brackets | NHIF report
7 | HR Operations | Payroll Processing | Monthly payroll with PAYE, NSSF, WCF, SDL, NHIF deductions | Tax tables, contribution rates | Payroll summary, payslips | Jan – Mar 2025 (Wk 11 – 22) | TZS 30,000,000 | Complete
|  | Leave Management | Leave requests, approvals, balance tracking | Leave types, entitlements | Leave balance report
|  | Loan Management | Employee loans with installment deduction from payroll | Loan types, limits | Loan register
|  | Recruitment | Job postings, applications, interview scheduling, hiring | Recruitment stages | Recruitment pipeline report
|  | Training | Training programs, attendance, certification tracking | Training types | Training report
|  | Disciplinary Actions | Record warnings, suspensions, and disciplinary proceedings | Action types | Disciplinary report
|  | Timesheets | Staff timesheet capture per project/activity | Timesheet config | Timesheet report
|  | Supervisor Assignments | Assign supervisors to sites/teams | — | Assignment report
3 | VAT & Tax Compliance | Sales VAT Register | Track VAT on all sales invoices, auto-calculated | VAT rates config | Sales VAT report | Jan – Mar 2025 (Wk 13 – 20) | TZS 19,500,000 | Complete
|  | Purchase VAT Register | Track input VAT from supplier invoices | — | Purchase VAT report
|  | Auto-Assessed VAT | Handle reverse-charge VAT for imported services | Auto-assess rules | Auto-assessed VAT report
|  | Withholding Tax | Calculate and track withholding tax on payments | WHT rates | WHT report
|  | VAT Returns | Generate TRA-ready VAT return summaries | Filing periods | VAT return summary
11 | Expense Management | Expense Claims | Staff submit expenses with receipts for approval | Expense categories | Expense summary report | Feb – Mar 2025 (Wk 18 – 23) | TZS 13,000,000 | Complete
|  | Project Expenses | Track expenses against specific projects | Approval workflow | Project expense report
|  | Expense Approvals | Multi-level approval chain for expense claims | Approval levels | Approval status report
|  | Expense Categories | Categorize expenses for accounting and reporting | Category config | Category-wise report
19 | TRA Receipt Scanner | QR Code Scanner | Scan TRA fiscal receipt QR codes via mobile camera | — | — | Mar – Apr 2025 (Wk 20 – 26) | TZS 13,000,000 | Complete
|  | Receipt Verification | Auto-verify receipt data from TRA website | TRA API config | Scanned receipts log
|  | Data Extraction | Extract seller TIN, amount, VAT, date from receipts | — | Receipt data report
|  | Accounting Integration | Link scanned receipts to purchase VAT register | — | —
15 | Reports & Analytics | Financial Reports | P&L, balance sheet, cash flow, trial balance | Fiscal year, date ranges | 12 financial reports | Mar – Apr 2025 (Wk 24 – 30) | TZS 15,500,000 | Complete
|  | Project Reports | Progress, cost, schedule, material usage per project | Report filters | 10 project reports
|  | HR Reports | Payroll, leave, attendance, headcount summaries | — | 8 HR reports
|  | Procurement Reports | PO status, supplier performance, stock levels | — | 6 procurement reports
|  | Tax Reports | VAT, PAYE, NSSF, WCF, SDL, NHIF summaries | — | 10 tax reports
|  | Custom Report Builder | Filter and export data across any module | Saved filters | 8 custom reports
1 | Dashboard & Navigation | Main Dashboard | Revenue stats, project summaries, pending approvals, calendar events | Dashboard widgets config | Dashboard summary | Apr 2025 (Wk 26 – 30) | TZS 11,500,000 | Complete
|  | Sidebar Navigation | Role-based dynamic menu with expandable sub-menus | Menu visibility per role | —
|  | Quick Actions | Shortcuts to common tasks from dashboard cards | — | —
|  | Notifications Center | Real-time Pusher notifications for approvals and assignments | Notification preferences | —
| PHASE 1: 10 Modules | 63 Sub-Modules |  |  |  | Oct 2024 – Apr 2025 | TZS 177,000,000 | 10 Complete
PHASE 2 — Project Management & Client Services (Apr 2025 – Sep 2025)
# | Module | Sub Module | Short Description | Settings | Reports | Implementation Period | Price (TZS) | Status
6 | BOQ Templates | Template Management | Create reusable BOQ templates with sections and items | Template categories | — | Apr – Jun 2025 (Wk 28 – 36) | TZS 17,000,000 | Complete
|  | Section Templates | Hierarchical section nesting (unlimited depth) | — | —
|  | Item Library | Standard material and labour items with default rates | Unit types, item categories | Item library report
|  | Template Cloning | Clone templates to new projects with one click | — | —
4 | Project Management | Project Setup | Create projects with client, location, dates, budget, contract info | Project types, statuses | Project list report | May – Aug 2025 (Wk 30 – 44) | TZS 39,000,000 | Complete
|  | Project BOQ | Bill of Quantities with sections, materials, labour line items | BOQ templates | BOQ summary report
|  | Project Schedule | Gantt-style activity scheduling with milestones and dependencies | Schedule templates | Schedule report
|  | Site Reports | Daily/weekly site progress reports with photos | Report templates | Site report summary
|  | Material Requests | Request materials from BOQ with multi-level approval | Approval workflow | Material request report
|  | Project Documents | Upload drawings, permits, contracts per project | Document categories | —
|  | Project Progress | Track percentage completion per BOQ section | — | Progress report
|  | Project Financials | Revenue, costs, profit tracking per project | — | Project financial report
|  | Site Visits | Schedule, assign and reschedule project site visits | Visit config | Site visit report
|  | Construction Phases | Define construction phases per project | Phase config | —
|  | Structural Design | Staged structural design tracking per project | Design stages | Design report
|  | Service Design | Staged service (MEP) design tracking per project | Design stages | Design report
|  | Project Designs | Manage project design documents and feedback | — | —
|  | Team Members | Assign and manage project team members | Role config | Team report
|  | Project Comments | Threaded comments/notes per project | — | —
|  | Activity Log | Audit trail of project activity | — | Activity report
|  | Import / Export | Bulk import and export of project data | — | —
5 | Finance & Accounting | Chart of Accounts | Full hierarchical account structure (assets, liabilities, equity, revenue, expenses) | Account types, categories | Trial balance | Jun – Jul 2025 (Wk 34 – 40) | TZS 13,000,000 | Complete
|  | Journal Entries | Double-entry journal with multi-line debit/credit | Entry types | Journal entry report
|  | Bank Accounts | Manage company bank accounts and balances | Bank list | Bank balance report
|  | Bank Reconciliation | Match bank statements with system transactions | — | Reconciliation report
|  | Petty Cash | Track petty cash disbursements and replenishments | Petty cash limits | Petty cash report
|  | Payment Vouchers | Approve and process payments to suppliers and staff | Approval workflow | Payment voucher report
|  | Receipts | Record and issue receipts for incoming payments | — | Receipt register
|  | Financial Statements | Income statement, balance sheet, cash flow | Fiscal year config | P&L, Balance Sheet, Cash Flow
14 | Provision Tax | Provisional Tax Setup | Configure provisional tax installment schedules | Tax year config | Provision tax schedule | Jun – Jul 2025 (Wk 36 – 40) | TZS 9,000,000 | Complete
|  | Installment Tracking | Track quarterly provisional tax payments | Due dates | Payment status report
|  | Tax Computation | Calculate provisional tax based on estimated annual income | Computation rules | Tax computation report
13 | eSMS Integration | SMS Gateway | Send bulk SMS via integrated gateway (Beem Africa) | Gateway API config | SMS delivery report | Jul – Aug 2025 (Wk 38 – 44) | TZS 11,500,000 | Complete
|  | SMS Templates | Pre-defined message templates for common notifications | Template management | —
|  | Automated Notifications | Auto-send SMS for approvals, reminders, updates | Trigger rules | Notification log
|  | SMS History | Full log of all sent messages with delivery status | — | SMS history report
16 | Settings & Configuration | Company Setup | Company name, logo, TIN, address, letterhead | Company profile | — | Jul – Aug 2025 (Wk 40 – 44) | TZS 9,000,000 | Complete
|  | Roles & Permissions | Define roles with granular permission matrix | 25+ permission groups | Permission audit report
|  | Approval Workflows | Configure multi-level approval chains per document type | 20+ document types | Approval audit trail
|  | Numbering Sequences | Auto-numbering for invoices, POs, vouchers, etc. | Prefix and sequence config | —
|  | Email Configuration | SMTP setup for system emails and notifications | Email templates | —
|  | Backup & Maintenance | Database backup scheduling and system maintenance | Backup schedule | Backup log
1 | Dashboard & Navigation | Main Dashboard | Revenue stats, project summaries, pending approvals, calendar events | Dashboard widgets config | Dashboard summary | Aug – Sep 2025 (Wk 42 – 46) | TZS 6,500,000 | Complete
|  | Sidebar Navigation | Role-based dynamic menu with expandable sub-menus | Menu visibility per role | —
|  | Quick Actions | Shortcuts to common tasks from dashboard cards | — | —
|  | Notifications Center | Real-time Pusher notifications for approvals and assignments | Notification preferences | —
15 | Reports & Analytics | Financial Reports | P&L, balance sheet, cash flow, trial balance | Fiscal year, date ranges | 12 financial reports | Aug – Sep 2025 (Wk 44 – 50) | TZS 11,500,000 | Complete
|  | Project Reports | Progress, cost, schedule, material usage per project | Report filters | 10 project reports
|  | HR Reports | Payroll, leave, attendance, headcount summaries | — | 8 HR reports
|  | Procurement Reports | PO status, supplier performance, stock levels | — | 6 procurement reports
|  | Tax Reports | VAT, PAYE, NSSF, WCF, SDL, NHIF summaries | — | 10 tax reports
|  | Custom Report Builder | Filter and export data across any module | Saved filters | 8 custom reports
18 | Client Portal | Project Visibility | Clients view their project progress, photos, schedules | Portal access config | — | Sep – Oct 2025 (Wk 46 – 52) | TZS 21,000,000 | Complete
|  | BOQ Transparency | Clients see detailed BOQ breakdown of their project | Visibility settings | —
|  | Billing Access | Clients view invoices, payments, and account statements | — | Client statement
|  | Document Sharing | Share drawings, permits, contracts with clients | Sharing permissions | —
|  | Communication | In-portal messaging between client and project team | — | —
| PHASE 2: 9 Modules | 57 Sub-Modules |  |  |  | Apr 2025 – Sep 2025 | TZS 137,500,000 | 9 Complete
PHASE 3 — Advanced Operations & Mobile (Sep 2025 – Feb 2026)
# | Module | Sub Module | Short Description | Settings | Reports | Implementation Period | Price (TZS) | Status
8 | Billing & Invoicing | Invoices | Professional tax invoices with line items, VAT, discounts | Invoice numbering, templates | Invoice register | Oct – Nov 2025 (Wk 50 – 58) | TZS 24,500,000 | Complete
|  | Proforma Invoices | Quotation-style invoices before final billing | Proforma numbering | Proforma register
|  | Credit Notes | Issue credit notes against invoices for returns/adjustments | — | Credit note register
|  | Debit Notes | Additional charges billed to clients | — | Debit note register
|  | Payment Tracking | Track payments received against invoices | — | Aging report
|  | PDF Generation | Auto-generate branded PDF invoices for email/download | Company letterhead | —
10 | Procurement | Supplier Management | Supplier database with contact info, TIN, categories | Supplier categories | Supplier list report | Oct – Dec 2025 (Wk 52 – 60) | TZS 28,500,000 | Complete
|  | Supplier Quotations | Request and receive quotations from multiple suppliers | — | Quotation comparison
|  | Quotation Comparison | Side-by-side comparison of supplier quotes per item | — | Comparison report
|  | Purchase Orders | Generate POs from approved quotations with terms | PO numbering, terms | PO register
|  | Goods Receiving | Record received goods against POs with quantity verification | — | GRN report
|  | Stock Management | Track inventory levels per project/warehouse | Warehouse config | Stock level report
|  | Auto Purchase | Automated purchase generation from requests | Auto-purchase rules | Auto purchase report
|  | Supplier Targets | Set and track supplier targets & preparation | Target config | Supplier target report
|  | Material Inspection | Inspect received materials for quality/quantity | Inspection config | Inspection report
|  | Material Transfer | Transfer materials between sites/warehouses | — | Transfer report
|  | Material Inventory | Per-project material inventory tracking | Inventory config | Inventory report
4 | Project Management | Project Setup | Create projects with client, location, dates, budget, contract info | Project types, statuses | Project list report | Oct – Nov 2025 (Wk 52 – 56) | TZS 10,500,000 | Complete
|  | Project BOQ | Bill of Quantities with sections, materials, labour line items | BOQ templates | BOQ summary report
|  | Project Schedule | Gantt-style activity scheduling with milestones and dependencies | Schedule templates | Schedule report
|  | Site Reports | Daily/weekly site progress reports with photos | Report templates | Site report summary
|  | Material Requests | Request materials from BOQ with multi-level approval | Approval workflow | Material request report
|  | Project Documents | Upload drawings, permits, contracts per project | Document categories | —
|  | Project Progress | Track percentage completion per BOQ section | — | Progress report
|  | Project Financials | Revenue, costs, profit tracking per project | — | Project financial report
12 | Labor Procurement | Casual Labor Hiring | Register and hire casual/daily workers for projects | Labor categories | Labor hire report | Nov – Dec 2025 (Wk 56 – 64) | TZS 21,000,000 | Complete
|  | Daily Rate Management | Set and track daily rates per skill/trade | Rate templates | Rate comparison report
|  | Gang Management | Organize workers into gangs/teams for task assignment | Gang types | Gang productivity report
|  | Labor Attendance | Track casual worker daily attendance per site | — | Labor attendance report
|  | Labor Payments | Process casual labor payments based on attendance | Payment schedules | Labor payment report
|  | Labor Inspection | Inspect and verify labor work output | Inspection config | Labor inspection report
16 | Settings & Configuration | Company Setup | Company name, logo, TIN, address, letterhead | Company profile | — | Dec 2025 (Wk 58 – 62) | TZS 7,800,000 | Complete
|  | Roles & Permissions | Define roles with granular permission matrix | 25+ permission groups | Permission audit report
|  | Approval Workflows | Configure multi-level approval chains per document type | 20+ document types | Approval audit trail
|  | Numbering Sequences | Auto-numbering for invoices, POs, vouchers, etc. | Prefix and sequence config | —
|  | Email Configuration | SMTP setup for system emails and notifications | Email templates | —
|  | Backup & Maintenance | Database backup scheduling and system maintenance | Backup schedule | Backup log
17 | Attendance System | Biometric Integration | ZKTeco device sync for automated clock-in/out | Device IP, sync interval | Attendance report | Dec 2025 – Jan 2026 (Wk 60 – 66) | TZS 18,000,000 | Complete
|  | Daily Attendance | View and manage daily attendance records | — | Daily attendance report
|  | Overtime Tracking | Calculate overtime hours based on work schedules | Overtime rules | Overtime report
|  | Attendance Reports | Monthly summaries, late arrivals, absent days | Working hours config | Monthly attendance summary
15 | Reports & Analytics | Financial Reports | P&L, balance sheet, cash flow, trial balance | Fiscal year, date ranges | 12 financial reports | Jan – Feb 2026 (Wk 62 – 68) | TZS 13,000,000 | Complete
|  | Project Reports | Progress, cost, schedule, material usage per project | Report filters | 10 project reports
|  | HR Reports | Payroll, leave, attendance, headcount summaries | — | 8 HR reports
|  | Procurement Reports | PO status, supplier performance, stock levels | — | 6 procurement reports
|  | Tax Reports | VAT, PAYE, NSSF, WCF, SDL, NHIF summaries | — | 10 tax reports
|  | Custom Report Builder | Filter and export data across any module | Saved filters | 8 custom reports
1 | Dashboard & Navigation | Main Dashboard | Revenue stats, project summaries, pending approvals, calendar events | Dashboard widgets config | Dashboard summary | Jan – Feb 2026 (Wk 64 – 68) | TZS 6,500,000 | Complete
|  | Sidebar Navigation | Role-based dynamic menu with expandable sub-menus | Menu visibility per role | —
|  | Quick Actions | Shortcuts to common tasks from dashboard cards | — | —
|  | Notifications Center | Real-time Pusher notifications for approvals and assignments | Notification preferences | —
20 | Mobile App (Flutter) | Staff Dashboard | Revenue stats, project progress, approvals, calendar on mobile | — | — | Nov 2025 – Feb 2026 (Wk 56 – 70) | TZS 50,500,000 | Complete
|  | Client Dashboard | Client project overview with status and progress | — | —
|  | Project Details | 7-tab view: BOQ, schedule, gallery, reports, billing, documents, financials | — | —
|  | Offline Mode | Full offline capability with Drift SQLite, auto-sync on reconnect | Sync interval | —
|  | Dual Language | English and Swahili throughout the app | Language selection | —
|  | Push Notifications | Real-time alerts for approvals, tasks, updates | Notification preferences | —
| PHASE 3: 9 Modules | 57 Sub-Modules |  |  |  | Sep 2025 – Feb 2026 | TZS 180,300,000 | 9 Complete
PHASE 4 — Sales & Marketing Tools (Feb 2026 – May 2026)
# | Module | Sub Module | Short Description | Settings | Reports | Implementation Period | Price (TZS) | Status
21 | Field Marketing | Field Sessions | Create sessions by officer/area/date, auto-numbering (FS-YYYYMM-001) | Session config | — | Feb – Apr 2026 (Wk 70 – 76) | TZS 470,000 | Complete
|  | Visit Logging | Log business visits — name, location, phone, status, service tags, lead linking | Service list | Visit report
|  | Follow-up Management | Follow-up dates on visits + automated email reminders via cron | Email config | Follow-up report
|  | Monthly Targets | Per-officer visit & conversion targets with actual vs target progress | Target config | Target report
|  | Service Catalogue | Configurable list of services pitched in the field | Service config | —
|  | Statistics Dashboard | Conversion rates, totals by status, per-officer breakdown | — | Stats report
|  | Campaign Management | Campaigns with type, territory, budget, target leads, status lifecycle | Campaign types | Campaign report
|  | Field Activities | Log activities per campaign/territory — type, outcome, lead count | Activity types | Activity report
|  | Territory Management | Geographic zones, assigned agents, linked to campaigns & activities | Territory config | Territory report
22 | WhatsApp Marketing | Contact Management | Contacts with stages, service tags, campaign source, assigned officer | Stage config | Contact report | Apr – May 2026 (Wk 76 – 80) | TZS 250,000 | Complete
|  | Ad Campaign Tracking | WhatsApp ad campaigns — budget, lead count, ROI, status lifecycle | Campaign config | Campaign report
|  | Call Logs | Per-contact call history log | — | Call log report
|  | Label Management | Contact categorization via labels | Label config | —
|  | Reports | Conversion rates, source analysis, stage funnel | — | Marketing report
23 | Content Creator | Task Management | Full CRUD — title, description, deadline, platform, task type, priority | Task types | Task report | Feb – Apr 2026 (Wk 70 – 78) | TZS 595,000 | Complete
|  | Kanban Board | 4-column visual board (todo > in progress > in review > published) via AJAX | — | —
|  | Calendar View | Weekly calendar of tasks by deadline + crew schedule entries | — | Schedule report
|  | Task Progress Tracking | Progress states with automatic status transitions | — | Progress report
|  | Task Comments | Threaded comment thread per task | — | —
|  | Task Attachments | Multi-type file upload (images, video, PDF, design files) per task | Storage config | —
|  | Task Approval | Approve & publish workflow (approved_by, approved_at) | Approval config | Approval report
|  | Platform Targets | Monthly targets per platform (IG, TikTok, FB, LinkedIn, YouTube) | Platform config | Target report
|  | Crew Management | Crew panel with online / busy / away / offline status | — | Crew report
|  | Crew Workability | Per-member analytics — total, done, in-progress, overdue, workload % | — | Workability report
|  | Statistics Dashboard | Monthly metrics — total, published, overdue, videos, designs, on-time rate | — | Stats report
|  | Activity Ticker | Live feed of recent task actions (assigned/started/submitted/published) | — | —
24 | Calculators | Design Pricing Calculator | Interactive calculator — package (low/high rise), add-ons, special structures, multi-currency | Package config | — | Nov 2025 – Feb 2026 (Wk 58 – 70) | TZS 350,000 | Complete
|  | Site Visit Calculator | Location-based cost calculator — 6 preset cost fields, multi-currency | Location config | —
|  | Convert to Billing | Push calculator output to billing document (invoice/proforma/quote) | — | —
|  | Currencies | CRUD — name, symbol, code, rate to USD, base currency flag | Currency list | —
|  | Design Packages | CRUD — low/high rise categories, USD price, included services (JSON) | Package list | —
|  | Design Add-ons | CRUD — add-on name, price low-rise USD, price high-rise USD | Add-on list | —
|  | Special Structure Rates | CRUD — structure name, rate TZS per sqm | Rate config | —
|  | Site Visit Locations | CRUD — location name + 6 preset cost fields | Location list | —
25 | Architect Bonus Scheme | Bonus Task Management | CRUD — create tasks per architect/project, auto-numbering (BNS-0001), role-based visibility | — | Task report | Mar – May 2026 (Wk 72 – 80) | TZS 370,000 | Complete
|  | Task Acceptance & Start | Architect accepts task to start bonus clock; admin can force-start | — | —
|  | Bonus Scoring | Admin scores task — actual date, design quality (0.4-1.0), client revisions | — | Score report
|  | Bonus Calculation Engine | SP/DQ/CA formula, weighted performance score, final units, bonus amount, no-bonus rule | Weight config | Calc report
|  | Unit Tier Configuration | Budget-range tiers (min/max amount to max units). CRUD for tiers | Tier config | —
|  | Weight Configuration | Admin configures 3 scoring weights (schedule/quality/client) summing to 1.0 | Weight config | —
|  | Bonus Payment Tracking | Mark scored tasks as paid, enforce scored to paid status flow | — | Payment report
|  | Monthly Report | Per-architect summary — tasks count, total units, total bonus, avg performance | — | Monthly report
| PHASE 4: 5 Modules | 42 Sub-Modules |  |  |  | Feb 2026 – May 2026 | TZS 2,035,000 | 5 Complete
PHASE 5 — Platform Extensions & Growth (Nov 2025 – May 2026)
# | Module | Sub Module | Short Description | Settings | Reports | Implementation Period | Price (TZS) | Status
26 | Website / Landing CMS | Portfolio Projects | Public project showcase with amenities, images, device-id likes | Project content config | — | Apr – May 2026 | TBD | Complete
|  | Awards | Company awards and recognition entries | Award config | —
|  | Services | Public services catalogue for the landing site | Service config | —
|  | Statistics | Headline counters/stats on the landing site | Stat config | —
|  | About & Values | Company about section and core values | Content config | —
|  | Team Members | Public team and leadership profiles | Team config | —
|  | Posters | Promotional posters and banners | Poster config | —
27 | Sales & CRM | Lead Management | Leads with sources, statuses and assigned officer | Lead source/status config | Lead report | Jan – Apr 2026 | TBD | Complete
|  | Sales Daily Reports | Daily sales activity reporting per officer | Report config | Daily sales report
|  | Lead Follow-ups | Follow-up scheduling with automated cron email reminders | Email config | Follow-up report
|  | Client Sources | Track client acquisition channels | Source config | —
|  | Customer Acquisition Cost | CAC tracking and analysis | — | CAC report
|  | Client Concerns | Log and resolve client concerns | — | Concern report
28 | Asset Management | Asset Register | Fixed asset records with categories | Asset config | Asset register report | 2025 – 2026 | TBD | Complete
|  | Asset Properties | Per-asset attributes and valuation | — | —
29 | KPI Management | KPI Templates | Reusable KPI templates with sections | Template config | — | 2025 – 2026 | TBD | Complete
|  | KPI Reviews | Periodic staff KPI reviews with ratings | Review config | KPI review report
|  | Review Attachments | Evidence and attachments per review | Storage config | —
30 | Wakala | Wakala Management | Agency/agent records, balances and transactions | Wakala config | Wakala report | 2025 – 2026 | TBD | Complete
| PHASE 5: 5 Modules | 19 Sub-Modules |  |  |  | Nov 2025 – May 2026 | TBD | 5 Complete
| GRAND TOTAL | 30 Modules (38 phase-instances) |  |  | 238 Sub-Modules |  | TZS 496,835,000 + TBD | 38 Complete

## Implementation Phases
PHASE 1 — Foundation & Core Operations (Oct 2024 – Apr 2025)
# | Module | Sub-Modules | Key Deliverables | Activities | Dependencies | Timeline | Price (TZS) | Status
16 | Settings & Configuration | Company Setup, Roles & Permissions, Approval Workflows, Numbering Sequences, Email Configuration, Backup & Maintenance | System configuration & security | Roles, permissions, approvals, company setup | None (first module) | Oct – Nov 2024 (Wk 1 – 5) | TZS 17,000,000 | Complete
2 | Employee Management | Employee Records, Employee Documents, Emergency Contacts, Employment History, Employee Separation | Complete employee database | CRUD forms, document upload, profile system | Company Setup (16) | Oct – Dec 2024 (Wk 3 – 10) | TZS 14,500,000 | Complete
5 | Finance & Accounting | Chart of Accounts, Journal Entries, Bank Accounts, Bank Reconciliation, Petty Cash, Payment Vouchers, Receipts, Financial Statements | Full accounting system | Chart of accounts, journal entries, bank reconciliation | Company Setup (16) | Nov 2024 – Feb 2025 (Wk 5 – 16) | TZS 26,000,000 | Complete
9 | Statutory Compliance | PAYE Processing, NSSF Contributions, WCF Contributions, SDL Contributions, NHIF Contributions | PAYE/NSSF/WCF/SDL/NHIF processing | Tax table setup, contribution calculation, reports | HR module (7) | Dec 2024 – Jan 2025 (Wk 9 – 15) | TZS 17,000,000 | Complete
7 | HR Operations | Payroll Processing, Leave Management, Loan Management, Recruitment, Training, Disciplinary Actions | Payroll with statutory deductions | Payroll engine, leave/loan processing, recruitment | Employee Mgmt (2), Statutory (9) | Jan – Mar 2025 (Wk 11 – 22) | TZS 30,000,000 | Complete
3 | VAT & Tax Compliance | Sales VAT Register, Purchase VAT Register, Auto-Assessed VAT, Withholding Tax, VAT Returns | TRA-ready VAT registers | VAT calculation engine, register UI, filing reports | Finance module (5) | Jan – Mar 2025 (Wk 13 – 20) | TZS 19,500,000 | Complete
11 | Expense Management | Expense Claims, Project Expenses, Expense Approvals, Expense Categories | Expense tracking with approvals | Claim forms, approval workflows, project linking | Finance (5) | Feb – Mar 2025 (Wk 18 – 23) | TZS 13,000,000 | Complete
19 | TRA Receipt Scanner | QR Code Scanner, Receipt Verification, Data Extraction, Accounting Integration | TRA receipt scanning tool | QR scanner, TRA verification, data extraction | VAT module (3) | Mar – Apr 2025 (Wk 20 – 26) | TZS 13,000,000 | Complete
15 | Reports & Analytics | Financial Reports, Project Reports, HR Reports, Procurement Reports, Tax Reports, Custom Report Builder | Core financial & HR reports | Report templates, filters, PDF/CSV export | All Phase 1 modules | Mar – Apr 2025 (Wk 24 – 30) | TZS 15,500,000 | Complete
1 | Dashboard & Navigation | Main Dashboard, Sidebar Navigation, Quick Actions, Notifications Center | Working dashboard with widgets | UI design, API integration, role-based widgets | Roles & Permissions (16) | Apr 2025 (Wk 26 – 30) | TZS 11,500,000 | Complete
| 10 Modules | 53 Sub-Modules |  |  |  | Oct 2024 – Apr 2025 | TZS 177,000,000
PHASE 2 — Project Management & Client Services (Apr 2025 – Sep 2025)
# | Module | Sub-Modules | Key Deliverables | Activities | Dependencies | Timeline | Price (TZS) | Status
6 | BOQ Templates | Template Management, Section Templates, Item Library, Template Cloning | Reusable BOQ template library | Template CRUD, section nesting, item library, cloning | None | Apr – Jun 2025 (Wk 28 – 36) | TZS 17,000,000 | Complete
4 | Project Management | Project Setup, Project BOQ, Project Schedule, Site Reports, Material Requests, Project Documents, Project Progress, Project Financials | Full project lifecycle management | Project setup, BOQ, schedules, site reports, material requests | Finance (5), BOQ Templates (6) | May – Aug 2025 (Wk 30 – 44) | TZS 39,000,000 | Complete
5 | Finance & Accounting | Chart of Accounts, Journal Entries, Bank Accounts, Bank Reconciliation, Petty Cash, Payment Vouchers, Receipts, Financial Statements | Project-linked financials | Project cost tracking, payment vouchers, project P&L | Phase 1 Finance | Jun – Jul 2025 (Wk 34 – 40) | TZS 13,000,000 | Complete
14 | Provision Tax | Provisional Tax Setup, Installment Tracking, Tax Computation | Provisional tax tracking | Tax computation, installment tracking, reminders | Finance (5) | Jun – Jul 2025 (Wk 36 – 40) | TZS 9,000,000 | Complete
13 | eSMS Integration | SMS Gateway, SMS Templates, Automated Notifications, SMS History | SMS notification system | Gateway integration, templates, automated triggers | Company Setup (16) | Jul – Aug 2025 (Wk 38 – 44) | TZS 11,500,000 | Complete
16 | Settings & Configuration | Company Setup, Roles & Permissions, Approval Workflows, Numbering Sequences, Email Configuration, Backup & Maintenance | Project-related settings | Project types, approval chains, document categories | Phase 1 Settings | Jul – Aug 2025 (Wk 40 – 44) | TZS 9,000,000 | Complete
1 | Dashboard & Navigation | Main Dashboard, Sidebar Navigation, Quick Actions, Notifications Center | Project-aware dashboard | Add project widgets, progress charts, calendar events | Phase 1 Dashboard | Aug – Sep 2025 (Wk 42 – 46) | TZS 6,500,000 | Complete
15 | Reports & Analytics | Financial Reports, Project Reports, HR Reports, Procurement Reports, Tax Reports, Custom Report Builder | Project & procurement reports | Progress reports, BOQ reports, cost analysis | Project module (4) | Aug – Sep 2025 (Wk 44 – 50) | TZS 11,500,000 | Complete
18 | Client Portal | Project Visibility, BOQ Transparency, Billing Access, Document Sharing, Communication | Client self-service portal | Client login, project view, billing access, documents | Projects (4), Billing (8) | Sep – Oct 2025 (Wk 46 – 52) | TZS 21,000,000 | Complete
| 9 Modules | 48 Sub-Modules |  |  |  | Apr 2025 – Sep 2025 | TZS 137,500,000
PHASE 3 — Advanced Operations & Mobile (Sep 2025 – Feb 2026)
# | Module | Sub-Modules | Key Deliverables | Activities | Dependencies | Timeline | Price (TZS) | Status
8 | Billing & Invoicing | Invoices, Proforma Invoices, Credit Notes, Debit Notes, Payment Tracking, PDF Generation | Complete billing & invoicing | Invoice CRUD, credit/debit notes, payment tracking, PDF | Finance (5), Projects (4) | Oct – Nov 2025 (Wk 50 – 58) | TZS 24,500,000 | Complete
10 | Procurement | Supplier Management, Supplier Quotations, Quotation Comparison, Purchase Orders, Goods Receiving, Stock Management | End-to-end procurement pipeline | Supplier mgmt, quotations, POs, receiving, stock | Projects (4), Finance (5) | Oct – Dec 2025 (Wk 52 – 60) | TZS 28,500,000 | Complete
4 | Project Management | Project Setup, Project BOQ, Project Schedule, Site Reports, Material Requests, Project Documents, Project Progress, Project Financials | Advanced project features | Document management, progress tracking, financials | Phase 2 Projects | Oct – Nov 2025 (Wk 52 – 56) | TZS 10,500,000 | Complete
12 | Labor Procurement | Casual Labor Hiring, Daily Rate Management, Gang Management, Labor Attendance, Labor Payments | Casual labor workforce system | Hiring, rates, gangs, attendance, payments | Projects (4), HR (7) | Nov – Dec 2025 (Wk 56 – 64) | TZS 21,000,000 | Complete
16 | Settings & Configuration | Company Setup, Roles & Permissions, Approval Workflows, Numbering Sequences, Email Configuration, Backup & Maintenance | Final settings & optimization | Fine-tune all configs, backup, maintenance tools | All modules | Dec 2025 (Wk 58 – 62) | TZS 7,800,000 | Complete
17 | Attendance System | Biometric Integration, Daily Attendance, Overtime Tracking, Attendance Reports | Biometric attendance system | ZKTeco integration, sync engine, overtime calc | Employee Mgmt (2) | Dec 2025 – Jan 2026 (Wk 60 – 66) | TZS 18,000,000 | Complete
15 | Reports & Analytics | Financial Reports, Project Reports, HR Reports, Procurement Reports, Tax Reports, Custom Report Builder | All 54 report templates | Billing reports, procurement reports, labor reports | All modules | Jan – Feb 2026 (Wk 62 – 68) | TZS 13,000,000 | Complete
1 | Dashboard & Navigation | Main Dashboard, Sidebar Navigation, Quick Actions, Notifications Center | Full-featured dashboard | Add billing, procurement, attendance widgets | Phase 2 Dashboard | Jan – Feb 2026 (Wk 64 – 68) | TZS 6,500,000 | Complete
20 | Mobile App (Flutter) | Staff Dashboard, Client Dashboard, Project Details, Offline Mode, Dual Language, Push Notifications | iOS & Android mobile app | Flutter app, offline mode, dual language, push notifications | All web modules (API) | Nov 2025 – Feb 2026 (Wk 56 – 70) | TZS 50,500,000 | Complete
| 9 Modules | 51 Sub-Modules |  |  |  | Sep 2025 – Feb 2026 | TZS 180,300,000
| GRAND TOTAL |  |  |  |  | 70 Weeks | TZS 494,800,000